## Lead
Project Name : - Open MRS.com Group Number - 4 Team Lead- Priyanshu Dwivedi

## Status Track
Project Status Check Report Team
Sl no. | Employee ID | Name | Domain | Module | 06-Dec-23-Test Design-Manual Test Scripts | 07-Dec-23-Desiging-Selenium and TestNG Scripts | 08-Dec-23-Adding Extended Reports | 09-Dec-23-Automation Testing and Reporting | 10-Dec-23-Designing Cucumber Frame Work | 11-Dec-23-Designing Cucumber Scripts | 12-Dec-23-Adding Extend Reports | 13-Dec-23-Integrating the Project | 14-Dec-23-Preparing For PPT
1 | 2576338 | Darshan K J | Testing | Manage Service Types | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
2 | 2576485 | Kalal Abhilash | Testing | register a patient | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
3 | 2575816 | Priyanshu Dwivedi | Testing | Manage Appointment Blocks Page Testing and Capturing Vitals | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
4 | 2576391 | Shivam Singh | Testing | New Service Taps | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
5 | 2577199 | Suraj S Malwankar | Testing | Edit Registration | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
6 | 2576681 | Thummaginjala Siva Prasad | Testing | Login | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
7 | 2576047 | Mucherala Mallika | Testing | Capture Vitals for Patient | Completed | Completed | Completed | Completed | Completed | completed | Completed | Completed | Completed
8 | 2576986 | Thangellapally Bharath Kumar | Testing | FindPatient Record | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
9 | 2576275 | Padarthi Siri Manasa | Testing | Appointment Scheduling | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed

## Status Meeting
Status Meeting Progress Check
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2023-12-06 | 10:30 | a | 2:00 | a | 5:00 | a
2023-12-07 | 10:00 | a | 1:00 | a | 5:30 | a
2023-12-08 | 10:00 | a | 12:30 | a | 5:00 | a
2023-12-09 | 10:30 | a | 12:30 | a | 5:30 | a
2023-12-10 | 10:00 | a | 12:30 | a
2023-12-11 | 10:00 | a | 12:30 | a | 5:30 | a
2023-12-12 | 10:30 | a | 12:30 | a
2023-12-13 | 10:00 | a | 12:30 | a
2023-12-14 | 10:00 | a | 12:30 | a